## Sept 21
HSE Project Plan
Periode September 2021
No | Activity | Project Base & date | [6 empty] | Remark
|  | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Mobilisasi BTH to BPN | Project Base & date 24: BTH to BPN 08.00-17.00 | Sesuai dengan rencana
2 | Preparation Audit Document (Quality & HSE) | Project Base & date 25: Mess BPN 08.00-16.00 | Sesuai dengan rencana
3 | Visit to Mess Senipah & then to pendingin site (Only Visit) after that consider further take action | Project Base & date 26: Mess Senipah & Pendingin 08.00-17.00 | Sesuai dengan rencana
4 | FOIP deliver PPE to Pak Tony & waiting for approval POB by PHKT Management | Project Base & date 27: FOIP 08.00-12.00 | Sesuai dengan rencana
5 | Visit to SLB Site (Lifting & Tubular) and also conduting Internal Audit related HSE aspect & Quality | Project Base & date 27: SLB Site LFTG 13.00-17.00; Project Base & date 28: SLB Site OCTG 08.00-17.00 | Sesuai dengan rencana
6 | Visit to PSB (Internal Audit) | Project Base & date 28: PSB site (PHKT) 08.00-17.00 | Membuat laporan Internal Audit SLB di FOIP 08.00-17.00
7 | Visit to PSTB (Internal Audit) | Project Base & date 29: PSTB site (PHKT) 08.00-17.00 | Membuat laporan Internal Audit SLB di FOIP 08.00-17.00
8 | - Interview kandidat HSE will be placed PHKT Project - Preparation document audit ISO 9001:2015 ISP that will conduct on october 2021 | Project Base & date 30: FOIP 08.00-17.00 | FOIP Membuat Emergency Response Plan Covid 19 PHM Closing PPE Bulanan Mengirim laporan hasil internal audit SLB site
Actual
Plan
Delayed
| Prepared by | Project Base & date 29: Approved by
| Oki Wiranata | Project Base & date 29: Gratcia Simanjuntak
| (QHSE Officer) | Project Base & date 29: (QHSE Manager)

## Oct 21
HSE Project Plan
Periode October 2021
No | Activity | Project Base & date | [6 empty] | Remark
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | - Hand over document to new HSE project. - Still preparation for audit document ISO 9001:2015 | Project Base & date 1: FOIP 08.00-17.00 | Follow Up beberapa persyaratan terkait green zone area mess phm Membuat Peraturan mengenai covid 19 sesuai dengan prosedur covid phm
2 | Collect all document related HSE at PSB site | Project Base & date 2: PSB 08.00-17.00 | Observasi for Improvement & Audit
3 | Visit PSTB Base | Project Base & date 3: PSTB 08.00-17.00 | Observasi for Improvement & Audit
4 | Assessment Green Zone Mess Senipah | Project Base & date 4: Senipah 08.00-17.00 | Sesuai dengan rencana
5 | Mobilisasi BPN to BTH office | Project Base & date 3: Mob
6 | Report all activity to pak gratcia | Project Base & date 4: BTH-OFC; Project Base & date 5: BTH-OFC; Project Base & date 6: BTH-OFC; Project Base & date 7: BTH-OFC
Actual
Plan
Delayed
| Prepared by | Project Base & date 6: Approved by
| Oki Wiranata | Project Base & date 6: Gratcia Simanjuntak
| (QHSE Officer) | Project Base & date 6: (QHSE Manager)